## Slide 1: Fairtrade SMART Action Plan 2022 - 2024

## Slide 2: Fairtrade SMART Action Plan 2022 - 2024
Action | Specific | Measurable | Appropriate | Realistic | Time | Who is Responsible | Status
The Partnership has a working or coordinating group that meets regularly and formally leads on efforts to attain, or retain, Fairtrade University and College Award status. | Form a working group for the accreditation with a core team, and others to dip in and out where appropriate FT Working Group, SSC Meetings, Business Review Meetings | Completion of meetings | Mandatory Criteria MN001 (5 points) | Yes – Meetings are scheduled | Fortnightly and Termly | FN | Complete – FT Working Group, SSC & Business Review Meetings all take place regularly
The partnership has a SMART action plan on Fairtrade. | Publish progress against the SMART Action Plan on the Eat and Shop web pages. | Creation of action plan and publish on web pages. | Mandatory Criteria MN002 (10 points) | Yes - Ongoing | Termly | FN | Complete - Action plan created and will be updated regularly
The partnership has published a public commitment of intent to support and champion Fairtrade | Formed within the last two years signed by senior management across the organisations and retail and catering outlets. | Signed copy of policy | Mandatory Criteria MN003 (10 points) | Yes - Complete | Annual | FN / SL | Complete – Review in March 24

## Slide 3: Fairtrade SMART Action Plan 2022 - 2024
Action | Specific | Measurable | Appropriate | Realistic | Time | Who is Responsible | Status
Put on a series of events and promotions for Fairtrade Fortnight 2023 & 2024 | Promotions to run in retail outlets Fairtrade events and promotions to run in MP Forum across 2 weeks of Fairtrade Fortnight. | Completion of events with - Post-event feedback, Social media reach, Sales data | Mandatory criteria MN004 (10 points) | Yes | Annually – 2 weeks Feb/March | KD, RN, TOM’s | 2023 Complete 2024 Events will run in Sept 24
Devise and deliver a campaign on Fairtrade, Trade Justice or ethical consumption. | To run in partnership with students Veganuary – 2023/2024 | Marketing Plan, Social Media Posts, Photo evidence, Campaign reach, Evaluation of impact | Mandatory criteria MN005 (15 points) | Yes | Annually - January | KD | 2023 Complete 2024 Complete
Stock Fairtrade certified products – Tea, Coffee, Hot Chocolate, Chocolate, Cotton Clothing | All products stocked and working to increase the number of lines or items sold | Number of lines stocked, Number of items sold, Feedback from customers | Mandatory criteria MN006 (10 points) | Yes | Annual Review | RN / TOM’s | Complete

## Slide 4: Fairtrade SMART Action Plan 2022 - 2024
Action | Specific | Measurable | Appropriate | Realistic | Time | Who is Responsible | Status
Stock at least one Fairtrade certified line in at least two of these categories – Soft Drinks, Wine or Beer, Health & Beauty, Savoury Snacks & Nuts, Cut Flowers, Fruit, Cotton Face Masks. | Stock a Fairtrade Wine within the Retail shops and Stock Fairtrade Soft Drinks within both Cafes and retail shops | Sales reports, order histories, photo evidence | Mandatory criteria MN007 (10 points) | Yes | Annual Review | RN / TOM’s | Complete
There is up to date POS material in all relevant outlets, highlighting Fairtrade products and providing information on the benefits of Fairtrade. | Fairtrade Foundation POS Material – Postcards and Posters to be displayed along side Fairtrade Products. | Photographic evidence. | Mandatory criteria MN008 (10 points) | Yes | Annually – Reviewed at the start of term | FN / RN / TOM’s | Complete
Complete the survey from the NUS about Fairtrade – send to students across the Uni via web links and social media | Put survey on our website / send via social media channels | Completion of survey. We will make the results public by uploading them onto our website. | Mandatory criteria MN009 (5 points) | Yes | Annually – Survey live Nov 23 - Feb 24 | FN / KD | In progress

## Slide 5: Fairtrade SMART Action Plan 2022 - 2024
Action | Specific | Measurable | Appropriate | Realistic | Time | Who is Responsible | Status
Provide and publicise opportunities for students to investigate Fairtrade, Trade Justice, or Ethical Consumption as part of their course work or dissertations. | Make opportunities available via website / online links / social media posts. | evidence of a well-publicised list of opportunities via different channels | Mandatory criteria MN010 (5 points) | Yes | Termly | KD / RN | Insights groups are taking place termly - Complete
Provide and publish an annual report on the findings and actions of our SMART plan | This could be a formal report, or a more informal display of outcomes, for example a page of outcomes on a website. | Published report | Mandatory criteria MN011 (10 points) | Yes | Annually – Term 1 | FN / KD | Complete
The Students Union / University has one or more active policies, which supports Fairtrade, passed within the last three years and has published them online. | University Environment & Climate Emergency Policy, Modern Slavery Act Statement, SSA Terms | Policy documents and web links | Leadership and Strategy criteria LD001 / LD002 (10 points each) | Yes | Annually | FN | Complete

## Slide 6: Fairtrade SMART Action Plan 2022 - 2024
Action | Specific | Measurable | Appropriate | Realistic | Time | Who is Responsible | Status
There is active leadership on Fairtrade, trade justice and ethical consumption issues from one or more senior members of staff. | Positive outcomes, Fairtrade and ethical trade considerations within job role. | Details of positive outcomes. | Leadership and Strategy criteria LD005 (15 points) | Yes | Annually | SL | Complete
The partnership has included Fairtrade and ethical consumption in staff and/or student inductions. | Colleague Guiding Principles | Evidence of document | Campaigning & Influencing criteria CI001 (10 points) | Yes | Annually | DT / FN | Complete
Partnered with a local off-campus Fairtrade group, and work together on at least one project or campaign over the year. | Devon & SW Fairtrade Group – attend meetings and investigate the options of working together on a upcoming project. | Meeting minutes, e-mail correspondence | Campaigning & Influencing criteria CI004 (10 points) | Yes | Approx. 6 weekly meetings | BH / FN | Complete

## Slide 7: Fairtrade SMART Action Plan 2022 - 2024
Action | Specific | Measurable | Appropriate | Realistic | Time | Who is Responsible | Status
Collaborate with another aspiring Fairtrade University or College in achieving Fairtrade status. | Make contact with colleagues from other Universities to ask if they would like to become a Fairtrade University. | Evidence of e-mails, correspondence with Uni’s and SOS, joining the award programme. | Campaigning & Influencing criteria CI006 (15 points) | Yes | Sept / Oct 23 | RN / FN | Complete
Our work and support of Fairtrade has an effective and up to date web presence. | Ensure there is easy to find, constantly updated content on our Eat and Shop web pages | Links to web pages | Campaigning & Influencing criteria CI007 (5 points) | Yes | Annually | KD / FN | Complete
The partnership has utilised social media and other communication channels to communicate Fairtrade campaigns widely and successfully | Plan and deliver regular social medial posts to promote and communicate our commitment to Fairtrade. | Evidence of schedule, posts, post likes, shares, reach. | Campaigning & Influencing criteria CI008 (5 points) | Yes | Monthly | KD / FN | Complete

## Slide 8: Fairtrade SMART Action Plan 2022 - 2024
Action | Specific | Measurable | Appropriate | Realistic | Time | Who is Responsible | Status
Ensure there is a strong Fairtrade presence at Fresher's Fairs. | Eat and Shop stand with promotional material | Photo’s evidence, e-mail correspondence relating to plans in place | Campaigning & Influencing criteria CI010 (10 points) | Yes | Annually - September | RN / TOM’s | Complete
The partnership has proactively publicised Fairtrade widely as an option for communal tea, coffee, hot choc & sugar in staff offices. | Posters displaying Fairtrade options – can purchase FT products from the MP Forum shop | Evidence of posters | Procurement, Retail & Catering criteria PL001 (5 points) | Yes | Annually | FN | Complete
Catering providers offer Fairtrade certified products as standard in the following categories – Fruit, Juice, Tea, Coffee, Sugar, Chocolate, Wine | Fresh Ideas menus Event Exeter Menus | Evidence of menus and photos | Procurement, Retail & Catering criteria PL002 (10 points) | Yes | Annually | FN | Complete

## Slide 9: Fairtrade SMART Action Plan 2022 - 2024
Action | Specific | Measurable | Appropriate | Realistic | Time | Who is Responsible | Status
Capture Fairtrade sales data for the previous two academic years and report back to the Fairtrade Foundation. | Data reports from MCR to show sales | Evidence of reports and of sending to the foundation | Procurement, Retail & Catering criteria PL003 (15 points) | Yes | Annually – Term 1 | FN | In progress
The partnership has included terms in tender documents that reference Fairtrade | Hot beverage and main catering produce supplier tender documents | Evidence of tender documents | Procurement, Retail & Catering criteria PL004 (15 points) | Yes | Annually | SL/RN | Complete
Fairtrade is served as standard in Hospitality across all products which have a Fairtrade option available | Show what Fairtrade products we offer within hospitality | Evidence of menus purchase orders | Procurement, Retail & Catering criteria PL006 (10 points) | Yes | Annual Review | FN | Complete

## Slide 10: Fairtrade SMART Action Plan 2022 - 2024
Action | Specific | Measurable | Appropriate | Realistic | Time | Who is Responsible | Status
Sales promotions – discounts, competitions, loyalty cards are run on Fairtrade products periodically throughout the year across relevant retail outlets. | Barisca loyalty cards Competitions | Evidence of loyalty cards | Procurement, Retail & Catering criteria PL010 (5 points) | Yes | Annually | RN/KD/FN | Complete
Within the last year, the partnership has peer-reviewed another Fairtrade University | Set up Teams call within another Uni to peer review and talk about the award | Evidence of meeting and peer review notes | Research & Curriculum criteria RC004 (5 points) | Yes | Plan meeting for Term 2 | RN / FN | Complete
The partnership has identified positive outcomes for the wider community through its Fairtrade work | Work with local guiding unit to educated and promote Fairtrade | Evidence of meeting – greater awareness – learning - | Outcomes criteria OT004 (10 points) | Yes | Plan for Term 2 | FN | Complete